## Sheet1
TUL - TCAA REQUIREMENTS | COMMENTS | TUL - TCAA REQUIREMENTS | COMMENTS
0. Application Fee |  | 0. Application Fee | PLEASE SUBMIT APPLICATION FEE OF $250
1a. TCAA Application | Provided in zip file #1 | 1a. TCAA Application | SUBMITTED
1b. Construction Drawings | N/A | 1b. Construction Drawings | SUBMITTED
2. City of Tulsa\County Permits | N/A | 2. City of Tulsa\County Permits | PLEASE SUBMIT ELECTRICAL PERMIT WHEN RECEIVED
3. List of Suppliers | N/A | 3. List of Suppliers | N/A
4. Certificate of Insurance for all contractors working on site | Insurance instructions and example COI provided in zip file #4 | 4. Certificate of Insurance for all contractors working on site | PARTIAL, NEED COI FOR ELECTRICIAN
5. Contact List for construction project team | Template provided in zip file #5 | 5. Contact List for construction project team | SUBMITTED
6. Lien Waivers | Provide at END OF PROJECT | 6. Lien Waivers | Provide at END OF PROJECT
7. Construction Schedule highlighting major milestones | Example schedule provided in zip file #1 | 7. Construction Schedule highlighting major milestones | PLEASE PROVIDE SCHEDULE W/ EXPECTED START AND END DATES
8. Change Orders | Provide at END OF PROJECT | 8. Change Orders | Provide at END OF PROJECT
9. Utility Shutdown Request - if applicable to project | Provided in zip file #6 | 9. Utility Shutdown Request - if applicable to project | N/A
10. Copies of Contractor Licenses |  | 10. Copies of Contractor Licenses | PLEASE SUBMIT COPY OF LICENSE FOR ELECTRICIAN
11. FAA Form 7460-1 Air Space Study | Zip file #7 - Please fill out page #3 and return to me as soon as possible | 11. FAA Form 7460-1 Air Space Study | N/A
12. Security Plan | Instructions and Template provided in zip file #8 | 12. Security Plan | SUBMITTED

## Sheet2
TUL TCAA Requirements | Comments
TCAA Application | See attached file #2
Plans | Provide 100% construction drawings/Plans
City of Tulsa\County Permit | Please submit applicable permit when received
List of Suppliers | Template provided (Attached File #3). Provide contact information for all suppliers working on this project
Contractor contact information | Template provided (File # 4). Provide contact information all Contractors working on site
Certificate of Insurance | COI for all contractor that will be working on site, reference attached file #5: "TAIT Insurance Requirements" for more information.
Construction Schedule | Highlight major milestones
Security Plan | Security plan guidelines and template attached (File #6). Also see attached TUL Badge application form, if required (File #6a).
FAA Form 7460-1 Airspace Study | If applicable, please see attached template (File #7)
Utility Shutdown Request | If applicable (Attached File #8)
Contractor License | Please provide if applicable